## Scope-Schedule
Project Name: | BART Daly City Station - Construction of a Bus Layover Area
Implementing Agency: | BART
Project Location: | Daly City BART Station
Supervisorial District(s): | N / A
Project Manager: | Aron Rice
Phone Number: | (510) 287-4809
Email: | arice@bart.gov
Brief Project Description (50 words max): | In coordination with SFMTA, convert existing parking spaces into a bus layover area to accommodate increased Muni service.
Detailed Scope (may attach Word document): Please describe the project scope, benefits, coordination with other projects in the area (e.g. paving, MuniForward, Vision Zero), and how the project would meet the Prop AA screening and prioritization criteria as well as other program goals (e.g., short-term project delivery to bring tangible benefits to the public quickly). Please attach maps, drawings, photos of current conditions, etc. to support understanding of the project. | Due to the planned Spring 2016 increase in service of SFMTA's 14R line, BART & SFMTA have agreed to the need for expanding the bus layover area within the Daly City BART parking lot by reducing the number of paid automobile parking spaces. BART staff have worked with SamTrans and Muni to increase the amount of bus layover space at Daly City for nearly two years. Due to existing space constraints, SFMTA buses are directed to layover outside the BART station on De Long St. These coaches sometimes block the street and subject to citations issued by Daly City Police. It is proposed that BART absorb the parking revenue loss from the decrease in the number of paid parking spaces as the expected BART revenue generated from the additional 14R bus riders would cover the cost of the necessary improvements to accommodate the buses. BART is willing to implement the construction of this project. After a discussion of project needs and a review of the parking lot pavement, a preliminary design indicated the need to upgrade and strengthen the pavement (from 2" to 8") in key aisles of the parking lot and at the bus pads where the buses will park and layover. Based on similar recent work bids, the estimated cost of this project (including soft costs) is $550K. BART plans to implement this project in Fall 2016. SFMTA supports this project as it will directly help accommodate the planned increases in service on the 14R (from weekday peak-only to all day weekdays and weekends) by improving terminal operations and creating a dedicated layover location within the Daly City BART parking lot. SFMTA estimates that, with the increase in 14R service, total boardings and alightings at Daly City will increase by nearly 950 passengers a day. A quick calculation of the costs and benefits of the project for BART (weekdays only) came up with the numbers below. Basically that would be $0.84/new trip brought by the 14R in just the first year. The fare revenue associated with it would be nearly $1.1M/year which more than offsets the loss of parking revenue. The expanded all-day, seven-day a week service on the 14R will allow Daly City BART station users whose travel plans are currently constrained by either the parking lot fill time or the existing weekday peak 14R service hours to have greater transit options. These changes are consistent with the kind of access improvements promoted by BART's Access Policy. DETAILED SCOPE Due to the planned Spring 2016 increase in service of SFMTA's 14R line, BART & SFMTA have agreed to the need for expanding the bus layover area within the Daly City BART parking lot by reducing the number of paid automobile parking spaces. BART staff have worked with SamTrans and Muni to increase the amount of bus layover space at Daly City for nearly two years. Due to existing space constraints, SFMTA buses are directed to layover outside the BART station on De Long St. These coaches sometimes block the street and subject to citations issued by Daly City Police. It is proposed that BART absorb the parking revenue loss from the decrease in the number of paid parking spaces as the expected BART revenue generated from the additional 14R bus riders would cover the cost of the necessary improvements to accommodate the buses. BART is willing to implement the construction of this project. After a discussion of project needs and a review of the parking lot pavement, a preliminary design indicated the need to upgrade and strengthen the pavement (from 2" to 8") in key aisles of the parking lot and at the bus pads where the buses will park and layover. Based on similar recent work bids, the estimated cost of this project (including soft costs) is $550K. BART plans to implement this project in Fall 2016. SFMTA supports this project as it will directly help accommodate the planned increases in service on the 14R (from weekday peak-only to all day weekdays and weekends) by improving terminal operations and creating a dedicated layover location within the Daly City BART parking lot. SFMTA estimates that, with the increase in 14R service, total boardings and alightings at Daly City will increase by nearly 950 passengers a day. A quick calculation of the costs and benefits of the project for BART (weekdays only) came up with the numbers below. Basically that would be $0.84/new trip brought by the 14R in just the first year. The fare revenue associated with it would be nearly $1.1M/year which more than offsets the loss of parking revenue. The expanded all-day, seven-day a week service on the 14R will allow Daly City BART station users whose travel plans are currently constrained by either the parking lot fill time or the existing weekday peak 14R service hours to have greater transit options. These changes are consistent with the kind of access improvements promoted by BART's Access Policy.
Prior Community Engagement/Support (may attach Word document): Please reference any community outreach that has occurred and whether the project is included in any plans (e.g. neighborhood transportation plan, corridor improvement study, station area plans, etc.). Please describe how this project was prioritized. | An increase in service frequencies for the 14R was identified as part of MUNI Forward, https://www.sfmta.com/projects-planning/projects/muni-forward-0 14R community engagement and outreach is documented on the MUNI Forward website https://www.sfmta.com/sites/default/files/projects/2015/Project%20timeline.pdf These service increases have been prioritized via the MUNI Forward implementation process.
Partner Agencies: Please list partner agencies and identify a staff contact at each agency. | San Francisco Municipal Transportation Agency - Julie Kirschbaum; San Mateo County Transit District - Eric Harris
Type of Environmental Clearance Required: | Categorically Exempt
Only design engineering (PS&E), construction and related procurement are eligible for Prop AA funds.
Project Delivery Milestones | Status | Work | Start Date |  | End Date
Phase | % Complete | In-house, Contracted, or Both | Month | Calendar Year | Month | Calendar Year
Planning/Conceptual Engineering (typically 30% design) | 100%
Environmental Studies (PA&ED) | 100%
Design Engineering (PS&E) | 65%
R/W Activities/Acquisition | 100%
Advertise Construction |  | N/A |  |  | N/A | N/A
Start Construction (e.g. Award Contract) | 0% | both | October | 2016 | N/A | N/A
Open for Use | N/A | N/A | N/A | N/A | December | 2016
Comments

## Cost-Funding
Project Name: | BART Daly City Station - Construction of a Bus Layover Area
PROJECT COST ESTIMATE |  | Funding Source by Phase
Phase | Cost | Prop AA | Prop K | Other | Source of Cost Estimate
Planning/Conceptual Engineering | 0 | N/A
Environmental Studies (PA&ED) | 0 | N/A
Design Engineering (PS&E) | 0
R/W | 0 | N/A
Construction | 550000 | 550000 |  |  | 65% percent design
TOTAL PROJECT COST | 550000 | 550000 | 0 | 0
Percent of Total |  | 100% | 0% | 0%
PROP AA EXPENDITURES BY FISCAL YEAR (CASH FLOW)
| 15/16 | 16/17 | 17/18 | 18/19 | Total
Design Engineering (PS&E) |  |  |  | 0 | 0
Construction |  |  | 550000 | 0 | 550000
TOTAL BY FISCAL YEAR | 0 | 0 | 550000 | 0 | 550000
PROJECT FUNDING PLAN (ALL SOURCES FOR DESIGN AND CONSTRUCTION PHASES)
Funding Source | Planned | Programmed | Allocated | TOTAL |  | Total
SF Prop AA | 550000 |  |  | 550000 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
TOTAL | 550000 | 0 | 0 | 550000 |  | 0
Comments/Concerns